## Road Map
UniPath
|  |  | Release 1 |  | Release 2
Application Modules | Feature Backlog | Story Points | Iteration 1 - 03/04/22 | Iteration 2 - 04/01/22 | Iteration 3 - 04/22/22 | Iteration 4 - 05/13/22
Module 1 - Account management | 01.01 Account Authentication | 4
| 01.02 Account Summary | 3
| 01.03 Customer Support | 3
Module 2 - Buy/Sell Products | 02.01 Browse Products | 8 | X
| 02.02 Make Payment | 7 |  | X
| 02.03 Upload Products | 9 | X | X
02.04 Submit Rating
| 02.05 Post Review | 7 |  | X
Module 3 - Advertising | 03.01 Post Ad | 6 |  |  |  | X
| 03.02 Update Ad | 6 |  |  |  | X
| 03.03 Remove Ad | 5 |  |  |  | X
Module 4 - Loan Information | 04.01 Provide Document Checklist | 6 |  |  | X
| 04.02 Display loan recommendations | 7 |  |  | X
Module 5 - Map System | 05.01 List of various buildings
05.02 Directions to different buildings
05.03 Know your real time location
|  | VELOCITY: | 17 | 16 | 13 | 17

## Story Map
Epics |  | UniPath - User Story Map
Epic 1 - Account Management |  | Epic 1 - Account Management | Epic 2 - Buy/Sell Products | Epic 3 - Advertising | Epic 4 - Loan information | Epic 5 - Map System
Epic 2 - Buy/Sell Products | User Stories |  | 02.01 Browse Products
Epic 3 - Advertising |  |  | 02.03 Upload Products
Epic 4 - Loan information | [6 empty] | Iteration 1
Epic 5 - Map System |  |  | 02.02 Make Payment
02.03 Upload Products
|  |  | 02.05 Post Review |  |  |  | Iteration 2
04.01 Provide Document Checklist
[5 empty] | 04.02 Display loan recommendations |  | Iteration 3
03.01 Post Ad
03.02 Update Ad
|  |  |  | 03.03 Remove Ad |  |  | Iteration 4