## I3
Task # | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
1 | 03. Advertising | 3.01 | Post Ad | Implement ability to post the picture of an ad | 2022-04-03 | 2022-04-05 | 100% | Xinhao Huang
2 | 03. Advertising | 3.01 | Post Ad | Implement core functionality | 2022-04-03 | 2022-04-06 | 100% | Xinhao Huang
3 | 03. Advertising | 3.01 | Post Ad | Implement GUI requirments | 2022-04-03 | 2022-04-06 | 100% | Xinhao Huang
4 | 03. Advertising | 3.01 | Post Ad | Implement Et -Ex crosscut | 2022-04-06 | 2022-04-07 | 100% | Xinhao Huang
5 | 03. Advertising | 3.01 | Post Ad | Test the core functionality & GUI requirements | 2022-04-08 | 2022-04-10 | 100% | Along Zhang
6 | 03. Advertising | 3.01 | Post Ad | Test the Et-ex crosscut | 2022-04-08 | 2022-04-10 | 100% | Along Zhang
7 | 03. Advertising | 3.02 | Update Ad | Implement ability to update the ad information | 2022-04-09 | 2022-04-10 | 100% | Xinhao Huang
8 | 03. Advertising | 3.02 | Update Ad | Implement core functionality | 2022-04-11 | 2022-04-13 | 100% | Xinhao Huang
9 | 03. Advertising | 3.02 | Update Ad | Implement GUI requirements | 2022-04-13 | 2022-04-15 | 100% | Xinhao Huang
10 | 03. Advertising | 3.02 | Update Ad | Implement the Et-Ex crosscut | 2022-04-14 | 2022-04-16 | 100% | Xinhao Huang
11 | 03. Advertising | 3.02 | Update Ad | Test the core functionality & GUI requirements | 2022-04-15 | 2022-04-16 | 100% | Along Zhang
12 | 03. Advertising | 3.02 | Update Ad | Test Et - Ex crosscuts | 2022-04-15 | 2022-04-16 | 100% | Along Zhang
13 | 03. Advertising | 3.03 | Remove Ad | Implement the ability to close an ad | 2022-04-17 | 2022-04-18 | 100% | Xinhao Huang
14 | 03. Advertising | 3.03 | Remove Ad | Implement core functionality | 2022-04-18 | 2022-04-19 | 100% | Along Zhang
15 | 03. Advertising | 3.03 | Remove Ad | Implement GUI requirements | 2022-04-18 | 2022-04-19 | 100% | Xinhao Huang
16 | 03. Advertising | 3.03 | Remove Ad | Implement Et-Ex crosscut | 2022-04-20 | 2022-04-21 | 100% | Xinhao Huang
17 | 03. Advertising | 3.03 | Remove Ad | Test the core functionality & GUI requirements | 2022-04-22 | 2022-04-23 | 100% | Along Zhang
18 | 03. Advertising | 3.03 | Remove Ad | Test the Et-ex crosscut | 2022-04-24 | 2022-04-25 | 100% | Along Zhang
19 | UniPath | All | All | Develop Class and sequence diagrams | 2022-04-03 | 2022-04-10 | 100% | Xinhao Huang
20 | UniPath | All | All | Develop ER diagram | 2022-04-03 | 2022-04-15 | 100% | Sanket Bagul
21 | UniPath | All | All | Develop Use case specification | 2022-04-03 | 2022-04-15 | 100% | All
22 | UniPath | All | All | Develop Supplementary Requirements document | 2022-04-03 | 2022-04-12 | 100% | Saahiil Meswaanii
23 | UniPath | All | All | Develop Use case diagarm | 2022-04-03 | 2022-04-09 | 100% | Praneta Kasbe

## I4
Task # | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
1 | 04. Loan Information | 4.01 | Provide document checklist | Implement ability to browse through the checklist | 2022-04-29 | 2022-05-01 | 100% | Xinhao Huang
2 | 04. Loan Information | 4.01 | Provide document checklist | Implement core functionality | 2022-05-02 | 2022-05-03 | 100% | Xinhao Huang
3 | 04. Loan Information | 4.01 | Provide document checklist | Implement GUI requirements | 2022-05-04 | 2022-05-05 | 100% | Xinhao Huang
4 | 04. Loan Information | 4.01 | Provide document checklist | Test the core functionality & GUI requirements | 2022-05-06 | 2022-05-07 | 100% | Along Zhang
5 | 04. Loan Information | 4.02 | Display loan recommendations | Implement the page having hyperlinks to several websites | 2022-05-07 | 2022-05-08 | 100% | Xinhao Huang
6 | 04. Loan Information | 4.02 | Display loan recommendations | Implement core functionality | 2022-05-07 | 2022-05-08 | 100% | Xinhao Huang
7 | 04. Loan Information | 4.02 | Display loan recommendations | Implement GUI requirements | 2022-05-08 | 2022-05-09 | 100% | Xinhao Huang
8 | 04. Loan Information | 4.02 | Display loan recommendations | Test the core functionality & GUI requirements | 2022-05-10 | 2022-05-11 | 100% | Along Zhang