## I1
Task # | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
1 | 02. Buy/Sell Products | 2.01 | Browse Products | Implement ability to browse products | 2022-02-19 | 2022-02-22 | 80% | Xinhao Huang
2 | 02. Buy/Sell Products | 2.01 | Browse Products | Implement ability to search for products | 2022-02-20 | 2022-02-22 | 80% | Xinhao Huang
3 | 02. Buy/Sell Products | 2.01 | Browse Products | Implement Et-In crosscuts | 2022-02-21 | 2022-02-23 | 70% | Xinhao Huang
4 | 02. Buy/Sell Products | 2.01 | Browse Products | Implement product type crosscuts | 2022-02-21 | 2022-02-23 | 30% | Xinhao Huang
5 | 02. Buy/Sell Products | 2.01 | Browse Products | Implement core functionality | 2022-02-22 | 2022-02-23 | 30% | Xinhao Huang
6 | 02. Buy/Sell Products | 2.01 | Browse Products | Implement GUI requirements | 2022-02-23 | 2022-02-24 | 30% | Xinhao Huang
7 | 02. Buy/Sell Products | 2.01 | Browse Products | Test the core functionality & GUI requirements | 2022-02-22 | 2022-02-24 | 10% | Xinhao Huang
8 | 02. Buy/Sell Products | 2.01 | Browse Products | Test Et-in and Product type crosscuts | 2025-02-24 | 2022-02-25 | 10% | Xinhao Huang
9 | 02. Buy/Sell Products | 2.03 | Upload Products | Implement upload the details of the product | 2022-02-25 | 2022-02-27 | 30% | Xinhao Huang
10 | 02. Buy/Sell Products | 2.03 | Upload Products | Implement upload the picture of the product | 2022-02-25 | 2022-02-27 | 30% | Xinhao Huang
11 | 02. Buy/Sell Products | 2.03 | Upload Products | Implement choose category for your product | 2022-02-26 | 2022-02-28 | 30% | Xinhao Huang
12 | 02. Buy/Sell Products | 2.03 | Upload Products | Implement Et-In crosscuts | 2022-02-27 | 2022-03-02 | 30% | Xinhao Huang
13 | 02. Buy/Sell Products | 2.03 | Upload Products | Implement core functionality | 2022-02-27 | 2022-03-02 | 30% | Xinhao Huang
14 | 02. Buy/Sell Products | 2.03 | Upload Products | Implement GUI requirments | 2022-02-27 | 2022-03-02 | 30% | Xinhao Huang
15 | 02. Buy/Sell Products | 2.03 | Upload Products | Test the core functionality & GUI requirements | 2022-02-27 | 2022-03-03 | 0% | Xinhao Huang
16 | 02. Buy/Sell Products | 2.03 | Upload Products | Test Et-in crosscuts | 2022-02-27 | 2022-03-03 | 0% | Xinhao Huang

## I2
Task # | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
1 | 02.Buy/Sell Products | 2.02 | Make Payment | Implement ability to browse your order | 2022-03-05 | 2022-03-10 | 0% | Xinhao Huang
2 | 02.Buy/Sell Products | 2.02 | Make Payment | Implement ability to browse the buyer's address | 2022-03-05 | 2022-03-10 | 0% | Xinhao Huang
3 | 02.Buy/Sell Products | 2.02 | Make Payment | Implement core functionality | 2022-03-11 | 2022-03-15 | 0% | Xinhao Huang
4 | 02.Buy/Sell Products | 2.02 | Make Payment | Implement GUI requirments | 2022-03-11 | 2022-03-15 | 0% | Xinhao Huang
5 | 02.Buy/Sell Products | 2.02 | Make Payment | Test the core functionality & GUI requirements | 2022-03-22 | 2022-03-25 | 0% | Xinhao Huang
6 | 02.Buy/Sell Products | 2.05 | Post Review | Implement ability to post the review | 2022-03-16 | 2022-03-21 | 0% | Xinhao Huang
7 | 02.Buy/Sell Products | 2.05 | Post Review | Implement ability to read the review by other users | 2022-03-16 | 2022-03-21 | 0% | Xinhao Huang
8 | 02.Buy/Sell Products | 2.05 | Post Review | Implement core functionality | 2022-03-22 | 2022-03-25 | 0% | Xinhao Huang
9 | 02.Buy/Sell Products | 2.05 | Post Review | Implement GUI requirments | 2022-03-22 | 2022-03-25 | 0% | Xinhao Huang
10 | 02.Buy/Sell Products | 2.05 | Post Review | Implement the Product type crosscut | 2022-03-26 | 2022-03-31 | 0% | Xinhao Huang
11 | 02.Buy/Sell Products | 2.05 | Post Review | Test the core functionality & GUI requirements | 2022-03-26 | 2022-03-31 | 0% | Xinhao Huang
12 | 02.Buy/Sell Products | 2.05 | Post Review | Test Product type crosscuts | 2022-03-26 | 2022-03-31 | 0% | Xinhao Huang
13 | 02.Buy/Sell Products | 2.03 | Upload Products | Implement the Df-In crosscut | 2022-03-26 | 2022-03-31 | 0% | Xinhao Huang
14 | 02.Buy/Sell Products | 2.03 | Upload Products | Implement the Df-out crosscut | 2022-03-26 | 2022-03-31 | 0% | Xinhao Huang
15 | 02.Buy/Sell Products | 2.03 | Upload Products | Test the Df-in & Df-out crosscut | 2022-03-26 | 2022-03-31 | 0% | Xinhao Huang